## WR Tracker
Status | Transform / Project | WR Reference | Opp Name | TCV | Requirements and scope agreed | Proposal meets requirements | Business case and spend approved | Work request signed | WR/IWR Initator | KD Programme level owner | KD PM on PCR | Solutioner or programme finance lead | IBM Owner | Date IBM received Request from Kyndryl | IBM Submitted WR Date | Signed Date | Submitted after work start? | Start Date | End Date | Next Steps | Current Contract End Date | Current PO End Date / Forecasted Date for PO Consumption | Risk to Delivery
Yet to Respond | Project_7 | WR_001 | Opp_17 | 271484 | No | Yes | No | No | User_5 | Owner_3 | PM_5 | Finance_1 | IBM_1 | 2025-04-17 | 2025-04-22 | 2025-04-27 | Yes | 2025-04-27 | 2025-06-09 | Follow up / In progress | 2025-06-29 | 2025-07-19 | High
Yet to Respond | Project_1 | WR_002 | Opp_11 | 307870 | No | Yes | No | No | User_3 | Owner_4 | PM_1 | Finance_4 | IBM_1 | 2025-04-06 | 2025-04-11 | 2025-04-16 | Yes | 2025-04-16 | 2025-07-14 | Follow up / In progress | 2025-09-09 | 2025-09-29 | Low
Awaiting Client Response | Project_1 | WR_003 | Opp_2 | 379473 | No | Yes | No | No | User_3 | Owner_1 | PM_4 | Finance_1 | IBM_5 | 2025-02-20 | 2025-02-25 | 2025-03-02 | Yes | 2025-03-02 | 2025-08-03 | Follow up / In progress | 2025-09-05 | 2025-09-25 | High
Yet to Respond | Project_4 | WR_004 | Opp_1 | 67749 | Yes | No | Yes | Yes | User_8 | Owner_2 | PM_5 | Finance_3 | IBM_4 | 2025-06-22 | 2025-06-27 | 2025-07-02 | No | 2025-07-02 | 2025-08-08 | Follow up / In progress | 2025-09-05 | 2025-09-25 | Medium
On Hold | Project_6 | WR_005 | Opp_18 | 426732 | No | No | Yes | Yes | User_6 | Owner_3 | PM_5 | Finance_2 | IBM_5 | 2025-03-11 | 2025-03-16 | 2025-03-21 | No | 2025-03-21 | 2025-04-28 | Follow up / In progress | 2025-05-16 | 2025-06-05 | High
Yet to Respond | Project_6 | WR_006 | Opp_6 | 239310 | No | No | Yes | No | User_1 | Owner_3 | PM_5 | Finance_4 | IBM_2 | 2025-07-07 | 2025-07-12 | 2025-07-17 | Yes | 2025-07-17 | 2025-08-22 | Follow up / In progress | 2025-09-20 | 2025-10-10 | High
Awaiting Client Response | Project_5 | WR_007 | Opp_7 | 181928 | No | Yes | No | Yes | User_8 | Owner_3 | PM_4 | Finance_4 | IBM_3 | 2025-05-08 | 2025-05-13 | 2025-05-18 | Yes | 2025-05-18 | 2025-08-04 | Follow up / In progress | 2025-08-18 | 2025-09-07 | Low
Signed | Project_3 | WR_008 | Opp_17 | 434523 | Yes | Yes | No | No | User_3 | Owner_1 | PM_3 | Finance_1 | IBM_2 | 2025-04-22 | 2025-04-27 | 2025-05-02 | No | 2025-05-02 | 2025-08-08 | Follow up / In progress | 2025-09-02 | 2025-09-22 | High
On Hold | Project_1 | WR_009 | Opp_5 | 289822 | No | No | Yes | Yes | User_10 | Owner_5 | PM_3 | Finance_1 | IBM_1 | 2024-12-24 | 2024-12-29 | 2025-01-03 | Yes | 2025-01-03 | 2025-06-03 | Follow up / In progress | 2025-06-19 | 2025-07-09 | Low
Awaiting Client Response | Project_10 | WR_010 | Opp_17 | 316918 | No | Yes | No | Yes | User_8 | Owner_5 | PM_2 | Finance_3 | IBM_4 | 2025-07-02 | 2025-07-07 | 2025-07-12 | Yes | 2025-07-12 | 2025-12-05 | Follow up / In progress | 2026-01-18 | 2026-02-07 | High
Awaiting Client Response | Project_4 | WR_011 | Opp_1 | 474818 | Yes | No | Yes | No | User_6 | Owner_1 | PM_2 | Finance_4 | IBM_1 | 2024-12-22 | 2024-12-27 | 2025-01-01 | No | 2025-01-01 | 2025-04-24 | Follow up / In progress | 2025-05-26 | 2025-06-15 | Low
Awaiting Client Response | Project_2 | WR_012 | Opp_7 | 451923 | Yes | Yes | Yes | No | User_1 | Owner_1 | PM_4 | Finance_3 | IBM_4 | 2025-05-27 | 2025-06-01 | 2025-06-06 | Yes | 2025-06-06 | 2025-07-29 | Follow up / In progress | 2025-09-08 | 2025-09-28 | Medium
On Hold | Project_3 | WR_013 | Opp_5 | 480463 | No | No | Yes | Yes | User_8 | Owner_2 | PM_2 | Finance_2 | IBM_5 | 2025-06-02 | 2025-06-07 | 2025-06-12 | No | 2025-06-12 | 2025-10-12 | Follow up / In progress | 2025-11-13 | 2025-12-03 | High
On Hold | Project_7 | WR_014 | Opp_8 | 50492 | No | No | No | No | User_4 | Owner_4 | PM_2 | Finance_2 | IBM_5 | 2025-07-05 | 2025-07-10 | 2025-07-15 | Yes | 2025-07-15 | 2025-08-30 | Follow up / In progress | 2025-09-14 | 2025-10-04 | Low
Yet to Respond | Project_5 | WR_015 | Opp_14 | 239769 | Yes | Yes | No | Yes | User_6 | Owner_3 | PM_5 | Finance_1 | IBM_2 | 2025-03-20 | 2025-03-25 | 2025-03-30 | Yes | 2025-03-30 | 2025-09-16 | Follow up / In progress | 2025-10-12 | 2025-11-01 | Low
On Hold | Project_9 | WR_016 | Opp_12 | 97117 | Yes | Yes | No | Yes | User_7 | Owner_4 | PM_4 | Finance_5 | IBM_5 | 2025-04-24 | 2025-04-29 | 2025-05-04 | No | 2025-05-04 | 2025-08-20 | Follow up / In progress | 2025-09-27 | 2025-10-17 | High
Signed | Project_2 | WR_017 | Opp_12 | 203263 | Yes | Yes | Yes | No | User_6 | Owner_4 | PM_4 | Finance_2 | IBM_5 | 2025-06-17 | 2025-06-22 | 2025-06-27 | No | 2025-06-27 | 2025-08-05 | Follow up / In progress | 2025-08-23 | 2025-09-12 | Medium
On Hold | Project_5 | WR_018 | Opp_4 | 253662 | No | Yes | No | No | User_3 | Owner_3 | PM_5 | Finance_3 | IBM_4 | 2025-07-07 | 2025-07-12 | 2025-07-17 | Yes | 2025-07-17 | 2026-01-10 | Follow up / In progress | 2026-02-03 | 2026-02-23 | Medium
Awaiting Client Response | Project_6 | WR_019 | Opp_9 | 204337 | No | Yes | No | Yes | User_10 | Owner_1 | PM_2 | Finance_5 | IBM_3 | 2025-02-17 | 2025-02-22 | 2025-02-27 | No | 2025-02-27 | 2025-07-21 | Follow up / In progress | 2025-09-17 | 2025-10-07 | High
Yet to Respond | Project_1 | WR_020 | Opp_2 | 450842 | Yes | Yes | Yes | No | User_4 | Owner_2 | PM_1 | Finance_1 | IBM_2 | 2025-01-06 | 2025-01-11 | 2025-01-16 | No | 2025-01-16 | 2025-03-24 | Follow up / In progress | 2025-04-27 | 2025-05-17 | Medium
On Hold | Project_6 | WR_021 | Opp_15 | 370585 | Yes | No | No | Yes | User_9 | Owner_2 | PM_2 | Finance_1 | IBM_3 | 2025-06-19 | 2025-06-24 | 2025-06-29 | No | 2025-06-29 | 2025-12-21 | Follow up / In progress | 2026-01-10 | 2026-01-30 | Medium
On Hold | Project_1 | WR_022 | Opp_15 | 483459 | No | No | Yes | Yes | User_5 | Owner_1 | PM_1 | Finance_1 | IBM_1 | 2025-05-10 | 2025-05-15 | 2025-05-20 | No | 2025-05-20 | 2025-09-24 | Follow up / In progress | 2025-10-20 | 2025-11-09 | High
Signed | Project_6 | WR_023 | Opp_1 | 454170 | No | Yes | No | Yes | User_2 | Owner_5 | PM_5 | Finance_4 | IBM_4 | 2025-05-13 | 2025-05-18 | 2025-05-23 | Yes | 2025-05-23 | 2025-07-27 | Follow up / In progress | 2025-08-27 | 2025-09-16 | High
Awaiting Client Response | Project_3 | WR_024 | Opp_10 | 155518 | No | No | Yes | No | User_10 | Owner_1 | PM_4 | Finance_3 | IBM_2 | 2025-07-08 | 2025-07-13 | 2025-07-18 | No | 2025-07-18 | 2025-09-21 | Follow up / In progress | 2025-11-02 | 2025-11-22 | Medium
Awaiting Client Response | Project_4 | WR_025 | Opp_18 | 448082 | No | No | No | No | User_3 | Owner_5 | PM_1 | Finance_5 | IBM_1 | 2025-03-09 | 2025-03-14 | 2025-03-19 | No | 2025-03-19 | 2025-06-22 | Follow up / In progress | 2025-07-22 | 2025-08-11 | Low
Awaiting Client Response | Project_2 | WR_026 | Opp_13 | 104374 | Yes | No | Yes | No | User_2 | Owner_2 | PM_4 | Finance_1 | IBM_4 | 2025-01-19 | 2025-01-24 | 2025-01-29 | No | 2025-01-29 | 2025-06-03 | Follow up / In progress | 2025-07-21 | 2025-08-10 | High
On Hold | Project_7 | WR_027 | Opp_1 | 359693 | Yes | Yes | Yes | No | User_6 | Owner_5 | PM_3 | Finance_3 | IBM_3 | 2025-04-21 | 2025-04-26 | 2025-05-01 | No | 2025-05-01 | 2025-07-21 | Follow up / In progress | 2025-09-03 | 2025-09-23 | Medium
Yet to Respond | Project_1 | WR_028 | Opp_5 | 338223 | Yes | Yes | No | No | User_3 | Owner_5 | PM_1 | Finance_2 | IBM_5 | 2025-02-06 | 2025-02-11 | 2025-02-16 | No | 2025-02-16 | 2025-07-30 | Follow up / In progress | 2025-09-27 | 2025-10-17 | Low
Awaiting Client Response | Project_9 | WR_029 | Opp_11 | 368796 | Yes | No | No | No | User_5 | Owner_3 | PM_1 | Finance_5 | IBM_3 | 2025-01-23 | 2025-01-28 | 2025-02-02 | No | 2025-02-02 | 2025-05-15 | Follow up / In progress | 2025-06-23 | 2025-07-13 | Medium
Signed | Project_10 | WR_030 | Opp_12 | 113567 | Yes | Yes | Yes | Yes | User_4 | Owner_5 | PM_3 | Finance_3 | IBM_4 | 2025-06-16 | 2025-06-21 | 2025-06-26 | Yes | 2025-06-26 | 2025-09-05 | Follow up / In progress | 2025-10-02 | 2025-10-22 | Medium
Signed | Project_5 | WR_031 | Opp_7 | 407810 | No | No | No | No | User_4 | Owner_2 | PM_4 | Finance_2 | IBM_3 | 2025-07-03 | 2025-07-08 | 2025-07-13 | Yes | 2025-07-13 | 2025-08-20 | Follow up / In progress | 2025-10-01 | 2025-10-21 | Low
Yet to Respond | Project_1 | WR_032 | Opp_16 | 275695 | Yes | No | Yes | No | User_5 | Owner_3 | PM_4 | Finance_3 | IBM_4 | 2024-12-27 | 2025-01-01 | 2025-01-06 | No | 2025-01-06 | 2025-03-11 | Follow up / In progress | 2025-03-28 | 2025-04-17 | Medium
Signed | Project_6 | WR_033 | Opp_3 | 219321 | Yes | No | No | Yes | User_2 | Owner_1 | PM_4 | Finance_4 | IBM_4 | 2025-04-03 | 2025-04-08 | 2025-04-13 | Yes | 2025-04-13 | 2025-08-29 | Follow up / In progress | 2025-09-08 | 2025-09-28 | Low
On Hold | Project_1 | WR_034 | Opp_16 | 388559 | No | Yes | Yes | Yes | User_4 | Owner_5 | PM_1 | Finance_1 | IBM_1 | 2025-05-19 | 2025-05-24 | 2025-05-29 | Yes | 2025-05-29 | 2025-11-22 | Follow up / In progress | 2026-01-19 | 2026-02-08 | Low
Signed | Project_2 | WR_035 | Opp_2 | 451405 | Yes | Yes | Yes | Yes | User_5 | Owner_5 | PM_1 | Finance_5 | IBM_2 | 2025-04-01 | 2025-04-06 | 2025-04-11 | No | 2025-04-11 | 2025-07-20 | Follow up / In progress | 2025-09-01 | 2025-09-21 | Low
Awaiting Client Response | Project_2 | WR_036 | Opp_4 | 253390 | Yes | Yes | No | Yes | User_10 | Owner_1 | PM_5 | Finance_5 | IBM_1 | 2025-04-30 | 2025-05-05 | 2025-05-10 | No | 2025-05-10 | 2025-07-13 | Follow up / In progress | 2025-08-31 | 2025-09-20 | High
Awaiting Client Response | Project_9 | WR_037 | Opp_18 | 100024 | Yes | No | Yes | Yes | User_3 | Owner_4 | PM_2 | Finance_3 | IBM_4 | 2024-12-30 | 2025-01-04 | 2025-01-09 | Yes | 2025-01-09 | 2025-03-04 | Follow up / In progress | 2025-03-17 | 2025-04-06 | Medium
Yet to Respond | Project_7 | WR_038 | Opp_7 | 282786 | No | No | Yes | No | User_1 | Owner_4 | PM_2 | Finance_4 | IBM_2 | 2025-02-03 | 2025-02-08 | 2025-02-13 | No | 2025-02-13 | 2025-06-09 | Follow up / In progress | 2025-06-21 | 2025-07-11 | Medium
Awaiting Client Response | Project_1 | WR_039 | Opp_19 | 392985 | Yes | Yes | No | Yes | User_2 | Owner_4 | PM_4 | Finance_5 | IBM_2 | 2025-02-23 | 2025-02-28 | 2025-03-05 | No | 2025-03-05 | 2025-04-26 | Follow up / In progress | 2025-06-14 | 2025-07-04 | High
Yet to Respond | Project_3 | WR_040 | Opp_15 | 179560 | Yes | Yes | Yes | No | User_2 | Owner_3 | PM_2 | Finance_5 | IBM_5 | 2024-12-28 | 2025-01-02 | 2025-01-07 | Yes | 2025-01-07 | 2025-03-02 | Follow up / In progress | 2025-04-21 | 2025-05-11 | High
Yet to Respond | Project_10 | WR_041 | Opp_1 | 360174 | Yes | Yes | Yes | No | User_5 | Owner_4 | PM_5 | Finance_2 | IBM_3 | 2025-01-17 | 2025-01-22 | 2025-01-27 | Yes | 2025-01-27 | 2025-04-28 | Follow up / In progress | 2025-06-15 | 2025-07-05 | Medium
Awaiting Client Response | Project_8 | WR_042 | Opp_20 | 202142 | No | No | No | Yes | User_5 | Owner_5 | PM_1 | Finance_5 | IBM_4 | 2025-06-27 | 2025-07-02 | 2025-07-07 | No | 2025-07-07 | 2025-09-24 | Follow up / In progress | 2025-10-31 | 2025-11-20 | Medium
Yet to Respond | Project_6 | WR_043 | Opp_4 | 88843 | Yes | No | No | No | User_8 | Owner_1 | PM_5 | Finance_5 | IBM_4 | 2025-01-14 | 2025-01-19 | 2025-01-24 | Yes | 2025-01-24 | 2025-06-26 | Follow up / In progress | 2025-07-20 | 2025-08-09 | Medium
Yet to Respond | Project_9 | WR_044 | Opp_14 | 380635 | Yes | Yes | Yes | No | User_8 | Owner_5 | PM_4 | Finance_3 | IBM_4 | 2025-01-31 | 2025-02-05 | 2025-02-10 | No | 2025-02-10 | 2025-05-15 | Follow up / In progress | 2025-05-25 | 2025-06-14 | Medium
Yet to Respond | Project_3 | WR_045 | Opp_4 | 477530 | No | No | No | Yes | User_8 | Owner_1 | PM_5 | Finance_3 | IBM_3 | 2025-05-18 | 2025-05-23 | 2025-05-28 | No | 2025-05-28 | 2025-07-14 | Follow up / In progress | 2025-08-01 | 2025-08-21 | High
Yet to Respond | Project_1 | WR_046 | Opp_14 | 468443 | Yes | Yes | No | Yes | User_3 | Owner_1 | PM_4 | Finance_4 | IBM_3 | 2025-01-05 | 2025-01-10 | 2025-01-15 | Yes | 2025-01-15 | 2025-02-25 | Follow up / In progress | 2025-03-17 | 2025-04-06 | High
Awaiting Client Response | Project_9 | WR_047 | Opp_5 | 375283 | Yes | No | No | No | User_10 | Owner_2 | PM_3 | Finance_1 | IBM_4 | 2025-01-27 | 2025-02-01 | 2025-02-06 | Yes | 2025-02-06 | 2025-07-06 | Follow up / In progress | 2025-08-18 | 2025-09-07 | Low
Yet to Respond | Project_5 | WR_048 | Opp_7 | 474714 | No | No | No | No | User_3 | Owner_5 | PM_1 | Finance_5 | IBM_5 | 2025-05-24 | 2025-05-29 | 2025-06-03 | No | 2025-06-03 | 2025-10-25 | Follow up / In progress | 2025-11-13 | 2025-12-03 | Low
Signed | Project_4 | WR_049 | Opp_5 | 297050 | No | No | No | Yes | User_8 | Owner_3 | PM_1 | Finance_5 | IBM_5 | 2025-01-07 | 2025-01-12 | 2025-01-17 | Yes | 2025-01-17 | 2025-03-13 | Follow up / In progress | 2025-04-26 | 2025-05-16 | Medium
Yet to Respond | Project_6 | WR_050 | Opp_8 | 482202 | No | No | Yes | No | User_9 | Owner_3 | PM_4 | Finance_1 | IBM_1 | 2025-06-02 | 2025-06-07 | 2025-06-12 | No | 2025-06-12 | 2025-11-01 | Follow up / In progress | 2025-11-26 | 2025-12-16 | High